## CAS Objectives 2010
OBJECTIVES
CAS Objective Tracking |  |  | (DO NOT CHANGE!) |  |  |  | Off target
Broader Goal/Objective | Specific Tasks to achieve broader goal | Contact/lead | Draft target for discussion /review | Final target / date completed | Status | Comments | At risk
Charge 1: Promote state of the art methods and technologies benefitting applied statisticians | Microsite | Mark/Shari |  | Q4 | On target |  | Completed
| Invited Panel Discussion Session JSM 2013:Diverse Applications of Statistics - Are We Doing Enough in Creating Visibility? | Amarjot/Jennifer |  | Q3 | Completed
| Round Table Discussions | Marlene |  | Q3 | Completed
| Tutorial session on statistical collaboration skills at CSP tutorial session | Eric Vance |  | Q3
| Weighting to achieve balance - ENAR 2014 invited Session Organizer | Shari |  | Q3
| JSM 2013 session using videos to improve statistical consulting - organizer/chair | Eric Vance |  | Q3
| Google Consumer Survey…Paper 2013 JSM Proceedings | Erin
| Create a preliminary draft of 2014-2015 pilot mentor program | All |  | Q4 | On target
| Amstat News Article (November) | Eric Vance |  | Q4
| Amstat News Master's Corner Article (Jan) | Amarjot/ Jennifer/Sharon
| Chair serves on the review panel for JSM short courses as part of ASA CE Course Evaluation Subcommittee | Amarjot | Q4 | Q4
| Proposal for JSM 2014 Invited Session | Amarjot/Erin |  | Q3 | Completed
Charge 2: the visibility and recognition of applied statisticians within various fields of application | JSM2013 Social mixer | Amarjot, All |  | Q3 | Completed
| Create a 2013 pilot mentor program idea for membership initiative proposal | All |  | Q1 | Completed
| Menoting Proposal Write-up & Submission - proposal approved and funded | Erin/Marlene/Amarjot | Q1 | Q1 | Completed
| Mentoring Clearinghouse Effort & Microsite archival | Marlene, Mark |  | Q1-Q4 | On target
| Welcome Packet & Hands on Mentoring | Richard/ Erin/ Keith | Q2 | Q2 | Completed
| Survey Creation & Analyses | Richard/ Shari/ John | Q4
| Mentor-Mentee Matching | Eric/ Jennifer
| Communication with Mentors & Mentees | Erin, Eric, Richard |  | Q3
| Communications | Amarjot, Marlene, Eric, Erin
| Maintain a "Friends of CAS" email list. Sharing news and communications. | Eric, Amarjot, John |  |  | On target
| Master's Notebook - supplying articles each month (except Sept) | All |  |  | On target
| CAS Microsite | Mark, Shari |  | Q1-Q4 | On target
| Roundtable at JSM 2014 |  |  |  |  | postponed due to other activities.
| Recognition of potential ASA Fellows in applied areas |  |  |  |  | postponed due to other activities.
Charge 3: Coordinate with other ASA groups/units to ensure attention to the needs, priorities and career paths of applied statisticians | Participation in organizing committee for 2013/14 Conference on Statistical Practice, summarize surveys | Eric/ Jennifer/Keith /John |  |  | On target
| Submitted Member Initiative 2013 ( ) - was funded by ASA board | All |  |  | Completed
| Maintain a "Friends of CAS" email list. Sharing news and communications. | Eric/Amarjot/Erin |  |  | On target
| JSM2014 JSM invited session on mentoring (submited in collaboration with COM) | Amarjot/Erin | Q3 | Q3 | Completed
| Microsite | Mark/Shari |  |  | Completed
| Each CAS member to linked to one Committee/Section/Council as part of membership initiative efforts as follows: • COC Business meeting -Marlene • COS Business meeting -Eric • BOD- David M gave an update • Membership Council-Amarjot • COM-Amarjot. • COWIS-Marlene and Lynn • Caucus for Women in Statistics- Lynn • First-Timers Session -Ricahrd • Isolated Statisticians-Richard Morris w • Q&P Section-Erin • Accreditation (PStat) committee-Erin • CSP Steering Comm-Eric | All |  | 2013 Q2 | Completed
Charge 4: Increase awareness and promote careers in applied stats |  |  |  |  | Completed
| CAS Developed Mentoring Program pilot at CSP Planning | Eric/Jennifer |  | Q3 | Completed
| Participation in organizing for the annual Conference on Stat Practice | Eric/ John | Q2-Q3 | Q2-Q3 | Completed
| JSM2013 Social mixer | Amarjot/All | Q3 | Q3 | Completed
| Master's Notebook - supplying articles each month (except Sept) | All | Q1-Q4 | Q1-Q4 | On target
| Maintain a "Friends of CAS" email list. Sharing news and communications. | Eric/John/Amarjot | Q1-Q4 | Q1-Q4 | On target
| Create a 2014/2015 mentoring program (continued from 2013-2014) for broader implementation at CSP and ASA | All | Q4 2013- Q1 2014 |  | On target
| JSM2013 Accepted proposal for invited program. Diverse Applications of Statistics - Are We Doing Enough in Creating Visibility? | Amarjot/Jennifer | Q2-Q3 | Q3
| Microsite | Mark/Shari | Q4 |  | On target
Note on D3: Merck: Send draft to core team
Note on E3: Merck: Ready for release on BARDS web site

## Coding
Status Code
Off target | Substantially off target or unlikely to be achieved without assistance
At risk | Off target by 1Q or less
On target | On target
Completed | Delivered